## Sheet1
Change Request ID | Date submitted | Submitted By | Description | Reason /justification | Impact Analysis | Priority | Approval Status | Approved by & date
1 | 2026-06-12 | Exam Controller | online exam registration module for student | Reduce paperwork , Reduce queues , do not visit university as a inperson for registration | Core module, need databae,login/signup UI , Exam registration form ui | High | Approved | Project Manager 13-june-2026
2 | 2026-06-11 | Project Manager | Need admin Dashboard , Generate Report Students grade,download /export in excel format | Admin/Exam controller needs reports without any IThelp | Admin Dashboard , Export download Business logic | Medium | Approved | Project Manager 13-june-2027
3 | 2026-06-12 | IT Department | Add two factor authentication via emal for student login | Improve security and prevent unauthorized access | Require Authentication module , email integrration | High | Approved | Project Manager 13-june-2028
4 | 2026-06-13 | Student Affairs Department | Add online fee payment integration | Students can pay examination fee online without visiting campus | Payment gateway integration ,database changes ,transaction logic,security testing | High | Approved | Project Manager 13-june-2029